## Priority Work List
Sun Ranch Road Repair Priority List
Compiled from the Roads/Easements Committee's full drive-through of all Association roads (100% surveyed) September 2026
Priority | Segment ID | Plat | Issue Type | Location Detail | Fix Needed | Notes / Contingencies | Status | Cost Estimate
1 | LL6 | Lyman Lakes | Mud pit | Entire segment is bad | Grading and Gravel | Worst segment on the list. Also needs gravel long-term (see Gravel Needs tab) as part of the fix. | Not Started
2 | LL1 | Lyman Lakes | Potholes | Throughout segment | Grading and Gravel - Crown the road to shed water. |  | Not Started
3 | LL3 | Lyman Lakes | Washboarding, ruts | Throughout segment | Grading and Gravel |  | Not Started
4 | L2 | Lower Lyman | Mud pits (3 distinct bad areas) | Three specific bad areas as marked on map | Grading and Gravel at the 3 spots |  | Not Started
5 | CL2 | Cape Labelle | Washboarding | Throughout segment | Grading and Gravel | Same segment also needs gravel to the Marmot gate long-term (see Gravel Needs tab). | Not Started
6 | CL4 | Cape Labelle | Ruts | Small, localized area | Grading and Gravel |  | Not Started
7 | CL12 | Cape Labelle | Ruts / rough road | In the ravine and heading up toward Owl | Grading and Gravel (drainage likely needed given ravine location) |  | Not Started
8 | CL14 | Cape Labelle | Rough crossing | Where Main Road crosses the common area | Grading and Gravel |  | Not Started
9 | LL5 | Lyman Lakes | Potholes, ruts | Low spot (water standing) and stretch heading east up the hill toward Morina Way | Grading and Gravel. Grade the low spot so water no longer stands; regrade the hill stretch | Two distinct problem areas within this one segment. | Not Started
10 | LL10 | Lyman Lakes | Rough spots | A few bad spots, locations as marked on map | Grading and Gravel |  | Not Started
11 | CL15 | Cape Labelle | Rough road | Area as marked on map | Grading and Gravel | Scope depends on outcome of the Squirrel Road conversation — if resolved as expected, stop where the map indicates, eliminating ~300 ft of fixing. | Not Started
[7 empty] | Total Estimated Cost | 0
Estimate column (blue) is left blank to fill in as bids/quotes come in — the total above will recalculate automatically.

## Preventive Gravel Needs
Gravel Needed to Stave Off Future Expensive Fixes
Not urgent today, but graveling these now avoids bigger repair costs later
Segment ID | Plat | Issue | Gravel Need | Notes | Cost Estimate
LL4 | Lyman Lakes | Mud | Gravel needed
LL6 | Lyman Lakes | Mud (also #1 overall priority) | Gravel as part of the fix | See Priority Work List tab, Priority 1 — rock/regrade also required there.
LL8 | Lyman Lakes | Mud | Gravel needed
CL2 | Cape Labelle | Washboarding (also Priority 5) | Gravel to the gate at Marmot | See Priority Work List tab, Priority 5 — regrading also required there.
|  |  |  | Total Estimated Cost | 0

## Watch List (Not Prioritized)
Items on the Map or Radar, Not Yet in the Priority Queue
Location | Current Condition | Why It's Held / Watched | Action
Deer Road | Section in dire need of a fix (shown on map, not on the numbered list) | An access issue in that area may cause the road to be relocated. Fixing now could be wasted work. | Hold until the access/relocation question is resolved.
Dugout Way (Lyman Lakes) | Not shown on current map. Mostly in pretty good condition overall. | One structure currently being built up there; construction is slow and the owner does not come up in winter, so traffic is minimal for now. Some areas will need grading and gravel once the road sees regular traffic. No money needs to be spent yet, but this could become a real project and reshuffle priorities down the road. | No spend now. Monitor traffic/construction progress and add to the map and priority list once activity increases.

## Legend & Notes
Legend & General Notes
Abbreviation | Plat
CL | Cape Labelle
LL | Lyman Lakes (Upper)
L | Lower Lyman
General notes:
• Every road in the Association was driven and surveyed 100%
• Two work types recur throughout: GRADING (to shed water off the road surface) and GRAVEL/ROCK (brought in specifically for mud areas).
• The 'Priority Work List' tab is ranked 1 (worst) through 11 based on current condition and travel capacity impact.
• The 'Preventive Gravel Needs' tab covers spots that are manageable today but will become expensive fixes if gravel isn't added before they see more traffic/erosion.
• The 'Watch List' tab covers a known bad spot (Deer Road) that's intentionally on hold pending an access decision, and a road not yet on the map (Dugout Way) that's fine for now but worth tracking.
Cost Summary:
Priority Work List total | 0
Preventive Gravel Needs total | 0
Grand Total | 0